## User Stories
ITimeU User Stories
Nr | User story | Story points | Business value | ROI | Comments
1 | As a registrant I want to register athletes manually Baseline story | 3 | 5 | 1.6667
2 | As a time keeper I want to start a timer for the given race so that timing is possible. | 2 | 5 | 2.5
3 | As a time keeper I want to see the running timer for the given race so that I can follow the time and know that the timing works. | 1 | 3 | 3
4 | As a time keeper I want to be able to save the time as a certain point is passed. | 3 | 5 | 1.6667
5 | As a time keeper I want the time automatically saved during a race so I don't have to do it manually |  | 2
6 | As an administrator I want to register name and distance of a race. | 3 | 4 | 1.3333
7 | As a registrant I want to connect participants to the proper races. | 5 | 5 | 1
8 | As a registrant I want to assign a start number to each participant so that they can be uniquely identified in the event/competition. | 3 | 5 | 1.6667
9 | As a registrant I want to be able to print a list of participants in a club together with their start number, so that the clubs can give the start numbers to the participants. | 5 | 2 | 0.4
10 | As a registrant I want to register participant start numbers in a list as they cross the finish line so that we know which order they finished in | 2 | 5 | 2.5
11 | As an administrator I want to merge the time results and the order of the starting number at the finish, so I get a merged list with finishing time and the corresponding correct starting number |  | 5
12 | As a registrant I want to mark participants as present so that they can participate. | 2 | 3 | 1.5
13 | As a time keeper I want to stop a started timer for the given race so that timing stops. | 2 | 5 | 2.5
14 | As an administrator I want to register classes with unique names so that I can group participants. | 3 | 4 | 1.3333
15 | As a registrant I want to assign each participant to a single class so that they can run in races for the given class. | 2 | 4 | 2
16 | As a time keeper I want to reset a timer for the given race so that timing can be restarted from the beginning. | 2 | 5 | 2.5
17 | As an administrator I want to import a list of athletes and classes. | 13 | 4 | 0.30769
18 | As an administrator I want to import a list of races | 8 | 1 | 0.125
19 | As an administrator I want to be notified if something is going wrong during import so that I know what data didn't get imported |  | 2 |  | Could be checked manually I guess
20 | As an administrator I want to assign athletes to a race automatically when importing so I don’t have to do it manually | 8 | 3 | 0.375 | This should normally be part of the import, yes
21 | As a registrant I want to update information about existing participants so that their information is correct. | 3 | 5 | 1.6667
22 | As a registrant I want to be able to look up the athletes so that I can check if a particular athlete is in the list of participants. | 5 | 5 | 1
23 | As a speaker I want to see a list of present participants for a given race so that I can announce them. | 3 | 3 | 1
24 | As a speaker I want to see the initial result and the official result of the race so that I can announce them. | 3 | 3 | 1
25 | As an administrator I want to approve the initial result so that it becomes the official result. | 2 | 3 | 1.5
26 | As an administrator I want to mark participants with a status (disqualified(DSQ), did not show up/ did not start(DNS), did not finish(DNF)) so that I can sort them in the results. | 3 | 4 | 1.3333
27 | As an administrator I should not be able to sort participants below a certain age by time in the results. | 2 | 1 | 0.5 | A warning is enough
28 | As an administrator I want to be able to edit the result list so that any changes can be made | 5 | 5 | 1
29 | As a registrant I want to be able to register name and number of the person who receives the list of participants and numbers, so that we can reach them in case someone asks for the start numbers. |  | 1
30 | As an administrator I want to check that the participant's club has paid their fee so that the participant is eligible for the regional championship. | 2 | 2 | 1 | Group
31 | As an administrator I want to check that the participant is registered to his/her club so that the participant is eligible for the regional championship. | 2 | 1 | 0.5 | Group
32 | As a registrant I want to be warned if registering an already registered athlete, so that I can choose to make the registration or not. | 3 | 3 | 1
33 | As a speaker I want to see the running timer for the given race so that I can follow the time and know that the timing works. | 2 | 2 | 1
34 | As an administrator I want to store the result of the race so that I can access it later. | 3 | 5 | 1.6667
| As a registrant I want to look up athletes from a list of previously registered athletes and add them to the participant list so that I don't have to type them manually. |  |  |  |  | Not relevant since the system is going to be offline.
| As an administrator I want to import external lists of athletes so that any registrant can access them during manual registration of participants. |  |  |  |  | Not relevant since the system is going to be offline.
| As a spectator I want to see the running timer for the given race, so that I can follow the time. |  |  |  |  | Not relevant since the system is going to be offline.
| As a spectator I want to see the result in real time so that I can follow the event live. |  |  |  |  | Not relevant since the system is going to be offline.
User stories not estimated (but still very important fundamental requirement the system must fulfil)
| As an administrator I want to be able to run the timing part of the system without Internet connection so that I can use it in the field. |  | 5
| As an administrator I want to run parts of the functionality of the system on a separate computer so that I don't have to share a computer with other persons. |  | 4
| As an administrator I want to set up the system locally so that it is not affected by other administrators running the system other places. |  | 2

## User Stories Prioritizes By ROI
ITimeU User Stories
Nr | User story | Story points | Business value | ROI | Sprint | Comments
3 | As a time keeper I want to see the running timer for the given race so that I can follow the time and know that the timing works. | 1 | 3 | 3 | 1
2 | As a time keeper I want to start a timer for the given race so that timing is possible. | 2 | 5 | 2.5 | 1
10 | As a registrant I want to register participant start numbers in a list as they cross the finish line so that we know which order they finished in | 2 | 5 | 2.5 | 1
13 | As a time keeper I want to stop a started timer for the given race so that timing stops. | 2 | 5 | 2.5 | 1
16 | As a time keeper I want to reset a timer for the given race so that timing can be restarted from the beginning. | 2 | 5 | 2.5 | 1
15 | As a registrant I want to assign each participant to a single class so that they can run in races for the given class. | 2 | 4 | 2
35 | As a registrant I want to import atlethes from FriRes | 13
36 | As a registrant I want to import a startlist for a race from FriRes | 8
37 | As a registrant I want to import classes from FriRes | 8
38 | As a registrant I want to import races from FriRes | 8
39 | As a timekeeper I want to edit the timestamp list manually so I can correct errors during the race | 8 |  |  | 2
40 | As a registrant I want to edit the list with the order of the startnumbers at a checkpoint so I can correct errors during the race | 5 |  |  | 2
1 | As a registrant I want to register athletes manually Baseline story | 3 | 5 | 1.6667
4 | As a time keeper I want to be able to save the time as a certain point is passed. | 3 | 5 | 1.6667 | 1
8 | As a registrant I want to assign a start number to each participant so that they can be uniquely identified in the event/competition. | 3 | 5 | 1.6667
21 | As a registrant I want to update information about existing participants so that their information is correct. | 3 | 5 | 1.6667
12 | As a registrant I want to mark participants as present so that they can participate. | 2 | 3 | 1.5
25 | As an administrator I want to approve the initial result so that it becomes the official result. | 2 | 3 | 1.5
6 | As an administrator I want to register name and distance of a race. | 3 | 4 | 1.3333
14 | As an administrator I want to register classes with unique names so that I can group participants. | 3 | 4 | 1.3333
26 | As an administrator I want to mark participants with a status (disqualified(DSQ), did not show up/ did not start(DNS), did not finish(DNF)) so that I can sort them in the results. | 3 | 4 | 1.3333
7 | As a registrant I want to connect participants to the proper races. | 5 | 5 | 1
22 | As a registrant I want to be able to look up the athletes so that I can check if a particular athlete is in the list of participants. | 5 | 5 | 1
23 | As a speaker I want to see a list of present participants for a given race so that I can announce them. | 3 | 3 | 1
24 | As a speaker I want to see the initial result and the official result of the race so that I can announce them. | 3 | 3 | 1
28 | As an administrator I want to be able to edit the result list so that any changes can be made | 5 | 5 | 1
30 | As an administrator I want to check that the participant's club has paid their fee so that the participant is eligible for the regional championship. | 2 | 2 | 1 |  | Group
32 | As a registrant I want to be warned if registering an already registered athlete, so that I can choose to make the registration or not. | 3 | 3 | 1
33 | As a speaker I want to see the running timer for the given race so that I can follow the time and know that the timing works. | 2 | 2 | 1
27 | As an administrator I should not be able to sort participants below a certain age by time in the results. | 2 | 1 | 0.5 |  | A warning is enough
31 | As an administrator I want to check that the participant is registered to his/her club so that the participant is eligible for the regional championship. | 2 | 1 | 0.5 |  | Group
9 | As a registrant I want to be able to print a list of participants in a club together with their start number, so that the clubs can give the start numbers to the participants. | 5 | 2 | 0.4
20 | As an administrator I want to assign athletes to a race automatically when importing so I don’t have to do it manually | 8 | 3 | 0.375 |  | This should normally be part of the import, yes
17 | As an administrator I want to import a list of athletes and classes. | 13 | 4 | 0.30769
18 | As an administrator I want to import a list of races | 8 | 1 | 0.125
5 | As a time keeper I want the time automatically saved during a race so I don't have to do it manually |  | 2
11 | As an administrator I want to merge the time results and the order of the starting number at the finish, so I get a merged list with finishing time and the corresponding correct starting number | 8 | 5
19 | As an administrator I want to be notified if something is going wrong during import so that I know what data didn't get imported |  | 2 |  |  | Could be checked manually I guess
29 | As a registrant I want to be able to register name and number of the person who receives the list of participants and numbers, so that we can reach them in case someone asks for the start numbers. |  | 1
34 | As an administrator I want to store the result of the race so that I can access it later. | 3 | 5 | 1.6667